## A3
Department of Child Safety FY18 Strategy Deployment A3 | [6 empty] | Process Owner: Director McKay |  |  | Revision Date: 09/17/2017
Current Condition, Gaps and Needs (Updated 6/3/2017) | [5 empty] | FY18 Strategic Initiatives |  |  |  |  | Plan |  |  | Complete |  |  | On track |  |  | Risk |  | Behind
Project Management Type A= A3; P = Project Management
[6 empty] | Obj. | Strategic Initiatives | Key Action Summary | Team Lead | Metrics |  | FY18 - Q1 |  |  | FY18 - Q2 |  |  | FY18 - Q3 |  |  | FY18- Q4
[12 empty] | J | A | S | O | N | D | J | F | M | A | M | J
[6 empty] | 1 | Implement SAFE AZ Model | - Complete training for investigations and ongoing, and system stakeholders. - Implementation of SAFE AZ tools | K. Guffey | Increase in the use of In Home Services | P | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 1 | Implement statewide field standardization | - Complete implementation of statewide standard for ongoing-specialized units including case planning, transfers, and disclosures. - Implement management system elements into policy | S. Hintze | Complete 100% of standarization implementation for all offices | A | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 1 | Targeted permanency activities to reduce the number of children in OOH | - Utilization of contracted providers to assist with targeted permanency activities including proactive ongoing case management - Explore expansion of permanent guardianship | S. Hintze | Number of children in out-of home care | A | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 1 | Expansion of prevention and intervention services and supports | Enhancement and expansion of Care Portal, SENSE, Baby Boxes, Building Resilient Families, Fast Pass pilot | S. Smith | Increase the referral and utilization of specified preventative services | A | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 2 | Refine and implement the foster family recruitment process | - Develop a recurring process to identify and resolve geographic and demographic gaps in placement array | AD Foster Care Supports | Process developed and implemented (including targets/actual) for foster placements recruitment by license/cohort type | A | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 2 | Implement a standardized statewide placement process | -Standardize the placement process statewide, placement service authorization process and improve location of runaways | C. Ballard | Decrease % of children placed in congregate care as first placement Decrease % of children palced in congregate care | A | bar: FY18 - Q1 J to FY18 - Q2 N
[6 empty] | 2 | Improve supports to foster care providers | Development of process and infrastructure to provide kinship and foster care providers with improved training, improved supports and connectivity to services | AD Foster Care Supports | Distribute 100% of the Kinship stipend resources 95% of foster placements contacted via on boarding process | A | bar: FY18 - Q1 J to FY18 - Q2 N
Reflection on Last Year's Objectives | bar: FY18 - Q2 O to FY18 - Q2 N
Obj # | Objective: |  |  | Results/Issues | % Achieved | bar: FY18 - Q2 O to FY18 - Q2 N
1 | Avoid historic 10%+ O-O-H population growth through improving safety decisions, targeted activities and prevention work |  |  | Department realized a 12% OOH population reduction over the past 15 months. These gains along with the implementation of an intentional management system have prepared the system to focus on practice quality | 80% | 2 | Refine and implement partnerships with paid placements | - Define and implement roles and responsibilites for the Department HRSS providers including site visits and increased partnership | AD Foster Care Supports | TBD | A | bar: FY18 - Q1 J to FY18 - Q2 N
2 | Maintain Fiscal Responsibility |  |  | Department developed a structured budgeting and review process as well as implemented sustainable cost reduction initiatives to operate within operating allocation | 95% | bar: FY18 - Q2 N
[6 empty] | 2 | Expand Fostering Sustainable Connections IV-E Waiver Project | Expand Fostering Sustainable Connections by utilizing privatized providers | S. Blackburn | Expand waiver project per schedule | P | bar: FY18 - Q1 J to FY18 - Q2 N
3 | Improve employee retention |  |  | Department eliminated work load constraints in investigations and implemented a revised case work pay structure. Development of the on boarding experience finished FY17 in pilot phase. | 40% | bar: FY18 - Q2 O to FY18 - Q2 N
--- | --- |  |  | --- | --- | 3 | Refine and implement "on boarding" experience | Improve retention through improvement of employee on boarding , training and coaching of all case carrying staff and supervisors | K. Ross | % attrition for trainees within first 22 weeks | P | bar: FY18 - Q1 J to FY18 - Q2 N
--- | --- |  |  | --- | --- | bar: FY18 - Q2 N
[6 empty] | 3 | Define and implement leadership development program for all people leaders | - Improve retention through development of supervisors and Managers in both general management and leadership skillset - Establish a leadership succession development strategy | HR Greg | Accomplish monthly action items on time per the action plan baseline | P | [12 empty] | s | bar: FY18 - Q1 J to FY18 - Q2 N
5 Yr Agency Strategic Priorities | bar: FY18 - Q2 O to FY18 - Q2 N
Improve objective decision making in Investigations and Ongoing | [5 empty] | 3 | Establish a culture of safety and support for DCS staff | - Implement Safety Science in the onboarding/training process - Establish peer to peer support teams | C. Melsek J. Bilskie | Percent of employees involved in critical incident review that particpated in peer to peer support # of self referrals for peer to peer support | A | bar: FY18 - Q1 J to FY18 - Q2 N
Develop and retain a highly effective workforce that engages with child welfare partners to serve children and families | bar: FY18 - Q2 N
Reduce length of stay for children in out-of-home care | bar: FY18 - Q2 N
Provide a quality experience for children while in out-of-home care | [5 empty] | 3 | Develop and implement an employee engagement strategy | - Implement an employee recognition and engagement committee - Design and implement a job shadowing program | HR Greg | TBD | A | bar: FY18 - Q1 J to FY18 - Q2 N
Reduce recurrence of maltreatment by providing quality service | bar: FY18 - Q1 J to FY18 - Q1 S; FY18 - Q2 N
[6 empty] | 4 | Successfully deploy the mobile solution statewide | - Full deployment of mobile solution that supports investigations and ongoing - Implement access to run background checks while in the field | L. Jewell | Complete 100% of the IT isntallation plan by June 30, 2018 | P | bar: FY18 - Q1 J to FY18 - Q2 N
FY18 Strategic Objectives | bar: FY18 - Q2 N
Obj # | Exec Sponsor | Summary | Summary | bar: FY18 - Q2 N
1 | K. Guffey | Objective: | Improve timeliness to permanency |  |  | 4 | Design and implement safety assessment model in Guardian | - Further reinforce the SAFE AZ Model through automation | L. Jewell | Complete 100% of the IT isntallation plan by June 30, 2018 | P | bar: FY18 - Q1 J to FY18 - Q2 N
|  | Metric: | Increase the percentage of children achieving permanency through reunification within 12 months | bar: FY18 - Q2 O to FY18 - Q2 N
2 | M. Faust | Objective: | Increase the placement of children in a family like setting | bar: FY18 - Q2 O to FY18 - Q2 N
|  | Metric: | 1.) Decrease the number of placement moves per 1,000 care days 2.) Increase the percentage of care days spent in a family setting |  |  | 4 | Implement a data quality plan for Guardian | - Align data initiatives against data management practices and federal rules | L. Jewell | Complete 100% of the IT isntallation plan by June 30, 2018 | P | bar: FY18 - Q1 J to FY18 - Q2 N
3 | HR Greg | Objective: | Improve employee retention | bar: FY18 - Q2 N
|  | Metric: | Reduce agency employee turnover | bar: FY18 - Q2 N
4 | L. Jewell | Objective: | Develop and implement the agency IT infrastructure |  |  | 5 | Develop implementation strategy for behavioral health services | Development of a complete integration assessment, transition and recurring costs analsysis and legislative change requirements | M.Faust | Accomplish monthly action items on time per the action plan baseline | A | bar: FY18 - Q1 J to FY18 - Q2 N
|  | Metric: | Complete 100% of IT implementation plan | bar: FY18 - Q2 N
5 | M.Faust | Objective: | Develop implementation strategy for Behavioral Health services | bar: FY18 - Q2 N
|  | Metric: | Complete 100% of implementation strategy including legislation plan
DCS Vision |  | Children thrive in family environments free from abuse and neglect |  |  |  | Core Principles |  | Safety: All Arizona's children are safe and protected from harm Permanency: All Arizona's children live in safe, loving forever families Well-Being: All Arizona's Children are given the opportunity to thrive through support of strong families and their communities
DCS Mission |  | Successfully engage children and families to ensure safety, strengthen families, and achieve permanency
FY2017 has focused on creating capacity in the system permitting case workers to further engage with families to improve assessment quality, deliver services to famlies and improve the number of children achieving timely permanency. Significant gains have been made implementing the DCS Management System and the results have been seen throughout the department. Opportunities for improvement remain in several keys areas of the organization including further improvements in objective decision making, improvements in foster care placements, placement options and provider/placement supports. Additional opportunities exist to improve IT automation including data integrity and collection as well as pursuing integration of Behaviorial Health Service with Medical sevices.
- Inactive cases and open reports have both realized a 90%+ reduction
- WIth improvements in capacity realized, Department efforts are focused on improving assessment consistency and quality, and family engagement.
- OOH population has reduced for the first time since 2005. Population peaked at 19,044 children in February 2016, and fell to 16,931 in March 2017. Case loads have reduced throughout the state as a result of the reductions.
- Employee turn over remains a challenge despite efforts to improve performance. YOY performance improved in the second half the year but Jul-Sep seperations were too high to realize YOY improvement
Note on R8: DCSMASTER-00: - participate in automation process
Note on R11: DCSMASTER-00: - in policy, embed AMS elements in each area of policy that is impacted (not a stand alone AMS section) - include court timeframes in the standardization process (i.e. TPR) - documentation of compelling reason - add practice guidelines to field standardization process map - encorporate practice framework with field standardization - implement a prioritization process to align field standardization with IT support/needs (i.e. monthtly meeting with IT team)
Note on R14: DCSMASTER-00: - for the permanent guardianship, begin with focus on the tribes and American Indian children - Explore target permanency activities that addresses disproportionality
Note on R17: DCSMASTER-00: - closely monitor the rollout of tier 2 Care Portal in Pima County
Note on R20: DCSMASTER-00: -
Note on R23: DCSMASTER-00: - improve/standardize the field side of entering CHILDS placement information - improve the invoicing/payment process on the business side that maintains checks and balances for provider accountability - develop a monthly process to identify runaway trends (high risk) - develop a process of what to do when runaway is located and brought back into care (placement and service options, and targeted permanency)
Note on R26: DCSMASTER-00: - perform a needs assessment to identify tangible actions to take - what should the central office and field org structures look like to support foster care providers
Note on B27: Guffey, Katherine, S: WE completed much more than is listed here. There isn't room for all of it, and the results may not be observable, measurable, or existant, but it seems like we would want to communicate that we did what we said we were going to.
Note on R29: DCSMASTER-00: - for roles and responsiilites, include HRSS providers, adoption certification providers, and foster parent (PS-MAPP) trainers '- Establish a communication plan to improve the dissimination of information, services, and supports for foster care givers - Develop a kinship support structure - Standardize the onboarding experience for foster care providers - Develop a comprehensive list of services and supports for foster care providers
Note on R35: Michael Faust: -coaching based training model -classroom verse real world balance - must address procedures and soft skils not just policy - dedicated field trainers - CQTI+9+50 -consider shadowing before starting core - Test folks - Role of ASU +$4.5M -Insource/Outsource where missing skillset - Utilization of field space - right to say folks wont make it - CWTI has ownership of employee readiness - Progress Checklist -no additional regional specific training - some kind of cohort experience - geographic assessment -Supervisor Development - Standard work - Clinicals -Safety Decisions - family engagement -rotation for burned out employees - process and skills development
Note on B41: DCSMASTER-00: case review metrics, group into items
Note on B42: DCSMASTER-00: fewer Ombudsman complaints, reduction in turnover
Note on B43: DCSMASTER-00: duration
Note on B44: DCSMASTER-00: reduced placement changes case review (supporting plaement & general wellbeing)
Note on R44: DCSMASTER-00: - develop community partnerships/sponsorships - design a cross-functional shadowing program - develop employee engagement survey to define the needs - explore volunteer opportunities for DCS employees/teams to participate in
Note on R50: DCSMASTER-00: - have to be able to measure if effort was made and if safety assessment was completed

## Bowling Chart
Department of Child Safety - Strategy Deployment Score Card
Strategic Objectives/Initiatives | Metric | Owner | FY YTD | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Objective: Improve timeliness to permanency | Increase the percentage of children achieving permanency within 12 months | K. Guffey | See Tables
Initiative: Implement SAFE AZ Model
Initiative: Refine and implement state wide field standardization | Complete standardization as defined in the action plan in all 45 field offices | S. Hintze | 54% |  |  | 53% | 54% | 59% | 61% | 62% | 65% | 75% | 83% | 89% | 93% | 97% | 99%
|  |  | 54% | 45% | 53% | 53% | 54% | 58% | 60% | 66%
Project: Targeted permanency activities to reduce OOH Pop | Reporting Metric - Number of Children in Out of Home Care (60 day lagging metric) | S. Hintze | 81016 |  |  | 16635 | 16316 | 16150 | 16007 | 15908
Initiative: Expansion of the Office of Prevention | Number of Referrals (BRF -Building Resilient Family + Care Portal-SW Region) | S. Smith | 819 |  |  | 168 | 197 | 142 | 164 | 148
| Amount Spent (Healthy Family + BRF -Building Resilient Family ) |  | 5365647 |  |  | 78936 | 1343157 | 309735 | 2067124 | 1566695
Objective: Increase the placement of children in a family like setting | Decrease the number of placement moves per 1,000 care days | M.Faust | --- |  |  | --- | --- | --- | --- | --- |  | --- | --- | --- | --- | --- | ---
|  |  | --- |  |  | 3.04 | 3.19 | 2.9 | --- | --- | --- | --- | --- | --- | --- | --- | ---
| Increase the percentage of care days spent in a family setting | M.Faust | --- |  |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | --- | --- | --- | ---
[5 empty] | 77% | 77% | 76.9% | 75.9% | 75.5% | 74.98%
| % of children whose predominant placement type is in a family like setting (Kinship/Foster) | M.Faust |  |  |  | 79.33% | 79.69% | 79.79% | 79.43% | 79.31%
| % of children whose predominant placement type is in congregate care |  |  |  |  | 16.23% | 15.95% | 15.76% | 15.97% | 16.01%
Initiative: Refine and implement the foster family recruitment process | Process developed and implemented (including targets/actual) for foster placements recruitment by license/cohort type | G. Vanasse | 100% |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  |  | 100% |  |  | 100% | 100% | 100% | 100% | 100%
Initiative: Implement a standardized statewide placement process | Decrease % of children placed in congregate care as first placement | G. Vanasse | 22% |  |  | 22% | 22% | 22% | 20% | 20% | 20% | --- | --- | --- | --- | --- | ---
|  |  | 18.5% | --- | 25% | 26.2% | 24.7% | 23% | 26.7% | 19%
| Decrease % of children placed in congregate care |  | 14.5% |  |  | 15% | 14.5% | 14% | 13.5% | 13.06% | 12.5% | 12% | 11.5% | 11% | 10.5% | 10.5% | 10%
|  |  | 14.1% |  |  | 14.9% | 14.2% | 14.4% | 14% | 14.6%
| Total number of children in congregate care (actual number, no target) |  | 11742 | 2327 | 2563 | 2455 | 2328 | 2324 | 2342 | 2293
Initiative: Improve supports to foster care providers | Distribute 100% of the Kinship stipend resources (30-60 day lag) | G. Vanasse | 2004000 | 167000 |  | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000
|  |  | <<<< |  |  | 49924 | 48427 | 152305 | 151668
| # of Children receiving the Kinship Stipend |  | 26988 |  |  | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249 | 2249
|  |  | 10637 |  |  | 2081 | 2144 | 2031 | 2225 | 2156
| % of children receiving at least one health service that has been modified (60 day lag) | K.Mouw | 90% | 90% | 95% | 95% | 90% | 80% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
|  |  |  | 93% | 94% | 94% | 94% | 84% | 55%
| % of children receiving all services needing verification (60 day lag) | K. Mouw |  | 75% | 80% | 75% | 80% | 65% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 75%
|  |  |  | 76% | 80% | 70% | 81% | 65% | 47%
Initiative: Refine and implement partnerships with paid placements | TBD | G. Vanasse | --- |  |  | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
|  |  | --- |  |  | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
Initiative: Execute IV-E Waiver Demonstration Project | Cumulative # of Referral Completed by Family Engagement Specialists (3 FESs @ 3 4/FES/month) | S. Blackburn | 11 |  |  | 4 | 4 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 17 |  |  | 3 | 3 | 6 | 1 | 4
| # of Children Achieving less Restrictive placement |  | 65 |  |  | 18 | 0 | 19 | 3 | 25
Objective: Improve Employee Retention | Reduce employee turnover - Agency rolling 12 month turn over | Greg C. | 27% |  |  | 27% | 27% | 27% | 25% | 25% | 25% | 24% | 24% | 24% | 23% | 23% | 23%
|  |  | 26.54% |  |  | 27.27% | 26.54% | 26.17% | 26.26% | 24.2%
| DCS Specialists Only (rolling 12 month attrition for Specialists only) | Greg C. | 30% |  |  | 30% | 30% | 30% | 28% | 28% | 28% | 26% | 26% | 26% | 24% | 24% | 24%
|  |  | 32.05% |  |  | 32.86% | 32.05% | 31.73% | 32.11% | 29.67%
Initiative: Refine and implement "on boarding" experience | DCS staff (non-specialist w/ < 12 months tenure | Greg C | 84 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | 21 |  |  | 4 | 3 | 6 | 2 | 6
| DCS Specialists < 12 months tenure | Greg C | 44 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | 44 |  |  | 9 | 8 | 11 | 14 | 2
| DCS Specialists < 22 weeks tenure | Greg C. | 72 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  |  | 28 |  |  | 7 | 11 | 4 | 2 | 4
Initiative: Refine and Implement Management and Leadership development for all People Leaders | Accomplish monthly action items on time per the action plan baseline | Greg C. | 100% |  |  | 100% | 100% | 100% | 100%
|  |  | 100% |  |  | 100% | 100% | 100% | 100%
Initiative: Establish a culture of safety and support for DCS staff | Percent of staffed involved with critical incident get support | C. Melsek J. Bilskie | --- | --- | --- | --- | --- | --- | --- | --- | --- | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | --- | --- | --- | --- | --- | --- | --- | --- | ---
| Number of self referrals |  | --- | --- | --- | --- | --- | --- | --- | --- | ---
Initiative: Develop and implement an employee engagement strategy | TBD | Greg C. | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
|  |  | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
Objective: Develop and implement the Department's IT infrastructure | Complete 100% of the IT installation plan by June 30, 2018 | L. Jewell | See Individual Project Details
Initiative: successfully deploy the mobile solution | Complete 100% of the IT installation plan by June 30, 2018 | L. Jewell | 80% | 80% | 90% | 75% | 80% | 85% | 90% | 95% | 100% | --- | --- | --- | --- | --- | ---
|  |  | 80% |  |  | 79% | 80% | 87% | 87% | 95
Initiative: Design and implement safety assessment in Guardian | Complete 100% of the IT installation plan by June 30, 2018 | L. Jewell | 22% | 7% | 22% | 7% | 22% | 27% | 38% | 45% | 50% | 60% | 65% | 75% | 80% | 90% | 100%
[6 empty] | 3% |  | 35% | 10% | 41%
Initiative: Implement data quality plan for Guardian | Complete 100% of the IT Data governance and data quality plan by June 30, 2018 | L. Jewell | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 25% |  |  | 50% |  |  | 75%
|  |  | 0% |  |  | 0% | 0% | 0% | 0% | 0%
Initiative: Implement cloud first strategy | Maintain 90% of all DCS managed applications in the cloud by June 30, 2018 | L. Jewell | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 98% | 100%
Initiative: Implement cloud first strategy | Maintain 90% of all DCS managed applications in the cloud by June 30, 2018 | L. Jewell |  |  |  | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 100%
[8 empty] | 90% | 90% | 90%
Develop implementation strategy for behavioral health services | Complete 100% of the BH Integration strategy and implementation plan | M.Faust | 30% |  |  | 20% | 30% | 40% | 50% | 55% | 55% | 65% | 75% | 90% | 94% | 98% | 100%
|  |  | 30% |  |  | 20% | 30% | 50% | 55% | 55%
Italicized = Prelim data
Note on A3: Michael Faust: Statement should be written in a from "X" performance to "Y" Performance by when
Note on B3: Michael Faust: Statement should be written in a from "X" performance to "Y" Performance by when
Note on B8: Michael Faust: Measure as % complete (# of elements implemented x number of offices / total number of elements x number of offices)
Note on B21: Navarro, Robert P.: 3rd Tuesday of the Month is when that data is most accurate.
Note on B30: Huse, Kathleen, S (Katie): 60 day lag

## Metric change log
Metric Changelog
Use this log to document changes made to metrics over the course of the FY2017 reporting period
Date of Change | Change owner | Metric # | Metric Name: | Type of Change | Description of Change:
2017-08-25 | Navarro | Initiative: Improve supports to foster care providers | Distribute 100% of the Kinship stipend resources | Changed to Service month | 30 day lag / Percent of participation
2017-08-25 | HR Greg | Refine onboarding experience: Progress to be measured by the monthly washout rate |  | Percent of washout rate

## Metric Calcs
Objective: Improve Employee Retention | Monthly washout rate of the following: DCS Employees <1 year; DCS Specialists <1 year; DCS Specialists <22 weeks.

## Metric DEfinition (hidden)
Metric | Definition | Data Source
Maintain the OOH Population at or below 19,000 children through June 30, 2017 (60 day lagging metric)
Comply to implementation plan <5% deviation from baseline each month
Complete standarization as defined in the action plan in all 45 field offices by x.
Maintain the OOH Population at or below 19,000 children through June 30, 2017 (60 day lagging metric)
Increase the % of utilization of preventative services from x to y
Operate the Department at or below $950M in operating costs | Appropriated = Forecasted assuming forecasted Is cash basis less than actual appropriation
100% of the budget control meetings occurred on time
< 2557 kids in Congregrate placement | # of children in all congregate placements on the last day of the reporting period (or the first run of the database in the next period | OOH Report
Residential/Therapeutic/RTC Group Homes | # of children in residential/therapeutic/rtc congregate placements on the last day of the reporting period (or the first run of the database in the next period | OOH Report
Shelter Group Homes | # of children in emergency shelter congregate placements on the last day of the reporting period (or the first run of the database in the next period | OOH Report
# of useable beds
Duration to license new beds Foster Home Beds (in months)
Duration to license new beds Group home beds (in months)
SVO monthly cost from x to x by June 30, 2017
Contract - unit cost for the big 5 from x to y
Prog Dev - Complete x fidelity monitors per month starting in y
Prog Dev - achieve x compliance of the top 5 services (PA, SVO, Lab, Trans, Pscych)
Achieve Operating Cost Management - Office Goods/Supply Order Expenditures
Achieve Operating Cost Management - Temp/Contracted Staff
Achieve Fleet Management Cost Targets - Cost per mile
Achieve Fleet Management Cost Targets - POV reimb. Expenditures
Achieve Property Management - Cost per Square foot target
ASU Evaluation Output
Actual Savings as captured
Reduce employee turnover from 26.7% in FY2016 to 25% in FY2017
Achieve less than 1000 inactive cases on or before June 30, 2017
Achieve Less than 13,000 open reports on or before June 30, 2017
Complete implementation by 8/31/2016
Comply to implementation plan <5% deviation from baseline each month
Comply to implementation plan <5% deviation from baseline each month
Note on A3: Michael Faust: Statement should be written in a from "X" performance to "Y" Performance by when
Note on A6: Michael Faust: Measure as % complete (# of elements implemented x number of offices / total number of elements x number of offices)